## Sheet1
Objectives |  | Start | End | Duration | Work Progress
Tasks to be Covered | Discrete Tasks
Literature Review and Knowledge Gathering | Overview | 2025-01-24 | 2025-01-25 | 1
| Background Study | 2025-01-26 | 2025-01-29 | 3
| Review of Existing Papers | 2025-01-30 | 2025-02-14 | 15
| Analyzing Research Papers to Select Methods | 2025-02-14 | 2025-02-15 | 1
| Documentation | 2025-02-16 | 2025-02-17 | 1 | 20%
Data selection and Feature study | Search data in Open-Source Portals | 2025-02-18 | 2025-02-19 | 1
| Data Selection | 2025-02-20 | 2025-02-21 | 1
| Feature Study | 2025-02-21 | 2025-02-22 | 1
| Documentation | 2025-02-22 | 2025-02-23 | 1 |  | 45%
Data Analysis and Feature Selection | Tool Selection | 2025-02-24 | 2025-02-25 | 1
| Feature Analysis | 2025-02-26 | 2025-02-28 | 2
| Preparing Target Feature | 2025-02-28 | 2025-03-01 | 1
| Selecting data features | 2025-03-02 | 2025-03-04 | 2
| Algorithm Selection and Determining Evaluation Matrices | 2025-03-04 | 2025-03-06 | 2
| Preparing Algorithm Queue | 2025-03-06 | 2025-03-07 | 1
| Documentation | 2025-03-07 | 2025-03-08 | 1 |  |  | 50%
Prediction | Split data into Train and Test Sets | 2025-03-09 | 2025-03-10 | 1
| Tune the Algorithms (from the queue) | 2025-03-11 | 2025-03-16 | 5
| Prepare the Finally-Tuned Models | 2025-03-17 | 2025-03-19 | 2
| Apply Models to predict Investment Trends | 2025-03-20 | 2025-03-25 | 5
| Determining the Optimum model | 2025-03-26 | 2025-03-28 | 2
| Test the Model | 2025-03-29 | 2025-03-31 | 2
| Determining Research Improvements by comparing Metrics | 2025-03-31 | 2025-04-04 | 4
| Documentation | 2025-04-04 | 2025-04-06 | 2 |  |  |  | 80%
Preparing Final Research documentation | Addressing Research Questions | 2025-04-07 | 2025-04-12 | 5
| Research Limitations and Future Scopes | 2025-04-13 | 2025-04-18 | 5
| Addressing Gaps and Challenges | 2025-04-18 | 2025-04-23 | 5
| Documentation | 2025-04-23 | 2025-04-28 | 5 |  |  |  |  | 90%
Final Project Report | Submission | 2025-04-30 | 2025-04-30 | 0 | [5 empty] | 100%
Formulas:
End = [Start]+1
End = [Start]
Duration = DAYS([End],[Start])
Start = [End, row above]+1
Start = [End, row above]